## Summary
CampusKart Mobile E-commerce QA Summary
Metric | Result | Severity | Count
Website | campuskart.site | High | 0
Executed test cases | 18 | Medium | 7
Passed | 9 | Low | 5
Passed with issues | 9 | Blocked/not tested | 8
Confirmed defects | 12
Release assessment
Core browsing, categories, cart calculations, seller navigation and mobile responsiveness worked. Release readiness is conditional because search clearing/navigation, seller identity display, cart badge synchronization, invalid-login feedback, and post-logout routing require correction. Payment, fulfilment and seller product management remain untested.
Test environment
Mobile browser; portrait and landscape orientations; buyer and seller accounts; execution date 17 September 2026. Desktop/tablet and financial transactions were not tested.

## Test Cases
ID | Area | Scenario | Steps / Test Action | Expected Result | Actual Result | Status | Linked Defect
BUY-001 | Buyer | Homepage loading | Open homepage and inspect visible UI plus Network requests. | Homepage loads with all main elements and no failed required resources. | Homepage loaded; manifest.json returned 404. | Passed with observation | BUG-001
BUY-002 | Buyer | Light and dark themes | Toggle theme, inspect readability, refresh. | Both themes remain readable and selection persists. | Both modes worked; selection persisted after refresh. | Passed
BUY-003 | Buyer | Product search | Search exact, partial, uppercase, nonexistent term, then clear input. | Correct results appear; clear restores catalogue. | Search cases worked, but clearing retained previous result. | Partially passed | BUG-002
BUY-004 | Buyer | Open product details | Open Jollof rice from search and category; view seller. | Selected product opens directly with correct details. | Search result opened Food & Drink; category card opened correct product. | Partially passed | BUG-003
BUY-005 | Buyer | Add quantity to cart | Set quantity 2, add to cart, refresh. | Subtotal is NGN800, seller is correct, cart persists. | Price and persistence worked; seller displayed Unknown Seller. | Partially passed | BUG-004
BUY-006 | Buyer | Update and remove cart item | Increase to 3, reduce to 0, refresh. | Totals update; zero removes item; empty state persists. | Subtotal and 9% fee updated; item removed; empty state persisted. | Passed
BUY-007 | Buyer | Empty cart and categories | Start shopping; open empty and populated categories; use Back. | Clear empty state, correct filters and navigation. | Books showed 0 products; Electronics showed 9; Back worked. | Passed
BUY-008 | Buyer | Multiple sellers and totals | Add Jollof rice and Airtel 5G ODU; inspect totals and badge. | Correct seller names, subtotal, delivery, fee, total and badge. | NGN45,236 total correct; seller names unknown; homepage badge stale. | Partially passed | BUG-004, BUG-005
BUY-009 | Buyer | Profile, orders and navigation | Open Profile and Orders; navigate bottom tabs. | Correct data, empty states and highlighted tabs. | Pages loaded, tabs highlighted and no freeze occurred. | Passed | BUG-006
BUY-010 | Buyer | Logout and invalid login | Sign out, use Back, submit invalid credentials, sign in. | Helpful login error and safe redirect after logout. | No invalid-login message; protected route showed persistent 404. | Partially passed | BUG-007, BUG-008
SELL-001 | Seller | Login and dashboard session | Log in, inspect seller menus, refresh. | Seller interface and session remain available. | Seller menus and zero-state product dashboard loaded; refresh retained session. | Passed
SELL-002 | Seller | Product access gating | Select Add Product with incomplete seller profile. | Unverified seller is redirected to profile completion. | Profile completion and identification requirements appeared. | Passed
SELL-003 | Seller | Profile validation | Test required fields, username and bio lengths. | Limits and supported-character rules provide clear feedback. | Required Save disabled; 250/50 limits enforced; symbols accepted without feedback. | Partially passed | BUG-009
SELL-004 | Seller | Navigation and empty states | Open Orders, Wallet, Profile, Messages, FAQ and Terms. | Each page loads, refreshes and navigates correctly. | All pages and empty states worked; Back and refresh worked. | Passed
SELL-005 | Seller | FAQ and legal controls | Search FAQ; open accordions; switch Terms/Privacy; refresh. | Clear no-result state; selected tab and theme persist. | Search and accordions worked; no-result message absent; Privacy reset to Terms. | Partially passed | BUG-010, BUG-011
SELL-006 | Seller | Role switching | Use Buy a Product, Start Shopping and Start Selling. | Correct flows open and seller session remains. | All role links worked and seller session remained. | Passed
SELL-007 | Seller | Logout and route protection | Sign out, use Back and refresh. | Confirmation appears and protected route redirects safely. | No confirmation; protected data blocked; persistent 404 shown. | Partially passed | BUG-008, BUG-012
RESP-001 | Shared | Mobile landscape responsiveness | Rotate buyer and seller pages to landscape and back. | Content remains readable and controls usable. | Both interfaces adjusted correctly in landscape. | Passed

## Bug Report
Bug ID | Severity | Priority | Status | Summary | Steps to Reproduce | Expected Result | Actual Result | Evidence
BUG-001 | Low | Low | Open | manifest.json returns 404 | Open homepage; DevTools Network; refresh. | Manifest returns 200 or is not requested. | manifest.json returned 404; shopping remained usable. | Homepage2.jfif
BUG-002 | Medium | Medium | Open | Clearing search does not restore products | Search Jollof rice; clear all text. | Default catalogue returns. | Previous search result remains under Search Results. | jollof3.jfif
BUG-003 | Medium | Medium | Open | Search-result product opens category page | Search Jollof rice; select result. | Jollof rice details page opens. | Food & Drink category page opens. | search(1).jfif
BUG-004 | Medium | High | Open | Cart displays Unknown Seller | Add product from named seller; open cart. | Correct seller name appears. | Unknown Seller appears for both tested products. | cart1.jfif; cart 4.jfif
BUG-005 | Medium | Medium | Open | Homepage cart badge is stale | Add products; return home; inspect cart icon; open cart. | Badge updates immediately on every page. | No badge on home until cart is opened. | cart error.jfif; cart 4.jfif
BUG-006 | Medium | Medium | Open | No way to add products to displayed Wishlist | Inspect product cards/details; inspect Profile Wishlist. | A visible Save/Wishlist control adds items. | Wishlist tab exists but no product save control is visible. | product.jfif; profile(1).jfif
BUG-007 | Medium | High | Open | Invalid login provides no error message | Submit incorrect buyer credentials. | Clear generic authentication error appears. | Form resets/returns without explanation. | login(1).jfif; login1.jfif
BUG-008 | Medium | High | Open | Logged-out protected routes show persistent 404 | Sign out as buyer or seller; press Back; refresh. | Redirect to login or public home. | 404 page appears and remains after refresh; protected data stays hidden. | back page.jfif
BUG-009 | Low | Medium | Open | Username allows unsupported characters without feedback | Enter spaces and symbols in seller username. | Characters are blocked or an inline error appears. | Characters remain with no visible inline warning. | bio2.jfif
BUG-010 | Low | Low | Open | FAQ search lacks no-results message | Search xyz987654 in Help & Support. | No matching questions message appears. | Questions disappear with no application message. | faq2.jfif
BUG-011 | Low | Medium | Open | Privacy tab resets to Terms after refresh | Open Privacy tab; refresh. | Privacy remains selected. | Terms tab is selected after refresh. | terms2.jfif; terms3.jfif
BUG-012 | Low | Low | Open | Seller logout has no confirmation | Seller menu; select Sign Out. | Confirmation appears before logout. | Seller is logged out immediately. | No screenshot; observed during execution

## Blocked Coverage
ID | Coverage Item | Status | Reason
SELL-B01 | Create a valid product | Blocked | Requires genuine seller identification and profile approval.
SELL-B02 | Edit, deactivate or delete product | Blocked | No approved seller product was available.
SELL-B03 | Moderation and product approval | Not tested | Requires administrator workflow and approval.
SELL-B04 | Receive and fulfil buyer order | Blocked | Requires an approved product and completed purchase.
SELL-B05 | Seller earnings and withdrawal | Not tested | No earnings; no financial action performed.
BUY-B01 | Wallet funding and payment | Not tested | No real payment or wallet funding performed.
BUY-B02 | Completed order tracking and rating | Blocked | Requires a completed transaction.
ENV-B01 | Desktop and tablet responsiveness | Not tested | Execution environment was a mobile phone.